## Sheet1
Team | 2023-11-28 | 2023-11-29 | 2023-11-30 | 2023-12-01 | 2023-12-04 | 2023-12-05 | 2023-12-06 | 2023-12-07 | 2023-12-08 | 2023-12-11 | 2023-12-12 | 2023-12-13 | 2023-12-14 | 2023-12-15 | 2023-12-18 | 2023-12-19
| Tuesday | Wednesday | Thursday | Friday | Monday | Tuesday | Wednesday | Thursday | Friday | Monday | Tuesday | Wednesday | Thursday | Friday | Monday | Tuesday
UI/UX | 2023-11-28: FINAL - NO WORK; 2023-12-01: Complete Prototype UI*; 2023-12-06: Drive API - "Link" GUI w/Drive**; 2023-12-13: (PM) Complete Final GUI; 2023-12-15: FINAL - NO WORK; 2023-12-19: No Work
QA | 2023-11-28: FINAL - NO WORK; 2023-12-01: Complete Test Cases; 2023-12-06: Complete Test Class; 2023-12-08: Test Invoker-Factory Interaction; 2023-12-13: (PM) Final Testing; 2023-12-15: FINAL - NO WORK; 2023-12-19: No Work
DEV | 2023-11-28: FINAL - NO WORK; 2023-12-01: Complete all Command classes; 2023-12-06: CommandFactory; 2023-12-08: (PM) Invoker-Factory Interaction; 2023-12-11: (QA) (UI/UX) (PM) Drive API - Executor ***; 2023-12-14: (PM) Assist w/Documentation; 2023-12-19: No Work
PM | 2023-11-28: FINAL - NO WORK; 2023-12-01: Complete Invoker event handling; 2023-12-06: Command History + GUI-Invoker Interaction (UI/UX); 2023-12-08: (DEV) Invoker-Factory Interaction; 2023-12-11: (QA) (UI/UX) (DEV) Drive API - Executor; 2023-12-14: Work on Presentation + (DEV) Documentation + (QA) Final Testing + (UI/UX) Final GUI; 2023-12-19: Present Project
* As Drive isn't linked, just use random and imaginary directories and files. ** GUI should accurately reflect all files and directories contained in Drive. This may be among the most difficult parts due to the research involved. *** Translate our Commands into actual actions done in Drive. Work with UI/UX and PM on the research. QA will assist with testing the code in the later phases of the project.